## Review Report
S. No. | Module | Role / User | Screen / Page | Category | Type | Description of Issue / Change
1 | Operations | Tansport Manager/ Karthik | Vehicle management | Missing | Feature | Cars (Crysta , Innova, Scorpio, Honda city, Kia)
2 | Operations | Tansport Manager/ Karthik | Vehicle management | Missing | Feature | Maintenace history complete list to be included. Partially available now ( FC, RC, Permit , Service history, Fast tag, PUCC)
3 | Operations | Tansport Manager/ Karthik | Vehicle management | Suggestion | Feature | Conductors name to be added, Student strength
4 | Operations | Tansport Manager/ Karthik | Route Management | Suggestion | Feature | Student count, Student name, Grade, Parent name, Contact number, Staff name , Staff number in each stop to be included. Already existing in Student trasport. This has to be mapped to Route management to view list of students and staff details under each route
5 | Operations | Tansport Manager/ Karthik | Assign duty | Suggestion | Feature | Vehicle type for pick up to be defined. Vehicle name as Car to be defined
6 | Operations | Tansport Manager/ Karthik | Vehicle Maintenance | Suggestion | Feature | Vehicle maintenance list to be added- Need to be sent from Transport manager.
7 | Operations | Tansport Manager/ Karthik | Request Approvals | Change | Feature | Fuel Request to be replaced as Fuel Management. Add Entry to be included ( in all task- not visible now)
8 | Operations | Tansport Manager/ Karthik | Transport Expenses | Suggestion | Feature | Previous Budget request to be included in the existing request. To be displayed as chart
9 | Operations | Tansport Manager/ Karthik | Transport Expenses | Suggestion | Feature | Add Fuel Expenses- Drop down . Inside , Outside to be added
10 | Operations | Tansport Manager/ Karthik | Transport Expenses | Suggestion | Feature | Drive and conductors daily attendance , leave, permission, OD and other details should be visible to the department head
11 | Operations | Tansport Manager/ Karthik | Transport Expenses | Suggestion | Feature | Drive and Conductors record which are maintained by HR should be reflected to Transport department heads
12 | Operations | IT Support Team Manager/ Sakthivel | Dashboard | Suggestion | Feature | IT Support - Raise ticket should be available to all users
13 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Suggestion | Feature | All details to be accessed through dashboard directly
14 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Change | Feature | Support Tickets- Update is duplicated. Need to remove the one located along with view under actions
15 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Change | Feature | Support to be renamed as Tickets
16 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Missing | Feature | To date option missing in all page
17 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | To add "Others" in drop down under all Categories
18 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | Assest Management- Add Assest- Repair, Damaged , Retired to be removed.
19 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | Support ticket - from User end option to be enabled and flow to be shown to the team
20 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | Frist level entries of data across departmnet should be uploaded by ERP team . Team will give details in excel only
21 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Missing | Feature | Template to be in downloadeble form
22 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Missing | Feature | Overall count of each categorywise Assest (KPIs) to be displayed
23 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | Quantity to be made visible . To be included in Excel format also
24 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Missing | Feature | Device Service history to be included
25 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Missing | Feature | Ticket history to be included
26 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Suggestion | Feature | Assest Transfer details- Particulars about assigning the assest to different departments
27 | Operations | IT Support Team Manager/ Sakthivel | Request Approvals | Suggestion | Feature | Quaotation Upload to be renamed as Comparitive Quotation upload
28 | Operations | IT Support Team Manager/ Sakthivel | Request Approvals | Suggestion | Feature | Comparitvie quotation template to be attached nearby for anyone to download and reload the document
29 | Operations | IT Support Team Manager/ Sakthivel | Request Approvals | Change | Feature | Vendor Propsal to be removed under Add request.
30 | Operations | IT Support Team Manager/ Sakthivel | Request Approvals | Suggestion | Feature | Purchase Order- PO to be included in all Budget related components across modules
31 | Operations | IT Support Team Manager/ Sakthivel | Request Approvals | Suggestion | Feature | Purchase Order- Process- To be included in all budget related categories.. ( 1. Comparitive quotation to be sent to Department head. 2. If minor purchase , department head will give approval without raising PO. / If Major purchase Department head to Escalate the request to MD. . 3.SLT to approve one quotation and ask the team to Raise PO. 4. Team to raise PO against SLT. 5. SLT to approve PO to proceed further)
32 | Operations | IT Support Team Manager/ Sakthivel | Announcement | Missing | Feature | Announcements- Add button to be included
33 | Operations | IT Support Team Manager/ Sakthivel | Announcement | Suggestion | Feature | S.no for all the reports
34 | Operations | IT Support Team Manager/ Sakthivel | Announcement | Suggestion | Feature | Total count quantity / concern to be displayed across modules
35 | Operations | IT Support Team Manager/ Sakthivel | Assest Management | Missing | Feature | Assest management category list to be included
36 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Missing | Feature | Complaint Status - Remark column to be added
37 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Missing | Feature | Outside service maintenance component to be included
38 | Operations | IT Support Team Manager/ Sakthivel | Support Tickets | Missing | Feature | Printer maintennance component to be added
39 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Dashboard | Suggestion | Feature | Assign Task to Housekeeping - Shalini/ Karthik/ Aduti-Process
40 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Task Management | Missing | Feature | To date option missing in all page
41 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Task Management | Missing | Feature | Duty allotment
42 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Duty Allotment tab | Missing | Feature | Schedule to be assigned
43 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Star of the month tab | Missing | Feature | Tabs to be added. Already given the flow. through DSR
44 | Operations | House Keeping Manager/ Arthi/ Muthukumar | RO Testing | Missing | Feature | Tabs to be added. Already given the flow. through DSR
45 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Lost and Found Entry | Missing | Feature | Tabs to be added. Already given the flow. through DSR
46 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Task Management | Missing | Feature | My Task - Remark column to be added
47 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Task Management | Missing | Feature | Fixed Schedules for daily, weekly, monthly to be reappear in the Task assigned on daily basis without assigning it every day. Only completion status to be updated by the respective incharge on daily basis
48 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Inventory- Stock Availablity and movement alone to be displayed . Entries not allowed.
49 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Stores- Inventories movement from stores to be made visible to House keeping
50 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Change | Feature | Minimum order , demand to be planned and given to stores management at the begining of the year. and it it to be set to Stores
51 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Inventory requirement tab to be added
52 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Duty allotment
53 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Schedule to be assigned ( Daily cleaning, Deep cleaning)
54 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | Janitor , Transport, other staff SOM , HR actions to be displayed under every staff profile
55 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Inventory | Missing | Feature | SOM for janitor- Access to House keeping supervisors to give scores
56 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Request Approvals | Missing | Feature | Rename Quotation and Comparitive quotation
57 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Announcement | Missing | Feature | Announcements- Add button to be included
58 | Operations | House Keeping Manager/ Arthi/ Muthukumar | Announcement | Missing | Feature | Announcements sending and receiving visibility not seen
59 | All | General | All | Missing | Feature | Renaming required- System Administration , Housekeeping , Cafeteria, Transport , Stores, Bus Management
60 | All | General | All | Missing | Feature | Task assingment and Communication from top to bottom , bottom to top both are same. Need to remove duplication
61 | Operations | Stationery / Shanmugavalli | Inventory | Suggestion | Feature | Stores- Inventories movement from stores to be made visible to all other respective department
62 | Operations | Stationery / Shanmugavalli | Request Approvals | Suggestion | Feature | Purchase Order- Process- To be included in all budget related categories.. ( 1. Comparitive quotation to be sent to Department head. 2. If minor purchase , department head will give approval without raising PO. / If Major purchase Department head to Escalate the request to MD. . 3.SLT to approve one quotation and ask the team to Raise PO. 4. Team to raise PO against SLT. 5. SLT to approve PO to proceed further)
63 | Operations | Stationery / Shanmugavalli | Request Approvals | Missing | Feature | Expiry date to be added
64 | Operations | Stationery / Shanmugavalli | Request Approvals | Suggestion | Feature | Filter options- 1. Category tab with all inventory list , 2. Monthly /Yeary tab 3. Departmentwise data should be made available both as Display and Downloadable excel
65 | Operations | Stationery / Shanmugavalli | Request Approvals | Suggestion | Feature | Requirement Tab to be added under each deparment which could be accessed by heads. Vendor name not required. Only Item, Qualntity , Requested by details to be included
66 | Operations | Stationery / Shanmugavalli | Reports | Suggestion | Feature | Search Option to be included in reports
67 | Operations | Stationery / Shanmugavalli | Reports | Missing | Feature | Product name also to be included under Expense report
68 | Operations | Stationery / Shanmugavalli | Reports | Missing | Feature | All announcement should be in two way communication
69 | Academic | Coordinator/ Gayathri | All | Missing | Feature | Time table change approval can be given to Principal alone.
70 | Academic | Coordinator/ Gayathri | All | Missing | Feature | Maintenace will have exclusive inventory
71 | Academic | Coordinator/ Gayathri | My Attendance | Missing | Feature | Attendance status filter- to change On leave to On Duty
72 | Academic | Coordinator/ Gayathri | Class Attendance | Suggestion | Feature | Newly dicussed -ESSL & Class mentor access to be given for discretions (Present, Absent, Half a day, OD ) and it should be visible to class mentor and coordinator
73 | Academic | Coordinator/ Gayathri | Class time table | Suggestion | Feature | Newly dicussed - Class time table and individual faculty time table should be visible
74 | Academic | Coordinator/ Gayathri | Class- Extended class | Suggestion | Feature | Add option to be removed under extended classes. Access for this to be given only to Principal'
75 | Academic | Coordinator/ Gayathri | Class time table | Suggestion | Feature | Time table- Filter to be added for all classes
76 | Academic | Coordinator/ Gayathri | Lesson Plan | Suggestion | Feature | Leeson plan template - Entry can be in any feasible format by the developer, but display should be visible in the template shared by QMIS
77 | Academic | Coordinator/ Gayathri | Unit Test | Missing | Feature | Unit Test to be brought under Student Evaluation
78 | Academic | Coordinator/ Gayathri | Unit Test | Missing | Feature | Unit Test to be renamed as CA (Continuous Assessment / RCT ( Regular Class Test)
79 | Academic | Coordinator/ Gayathri | Exam | Suggestion | Feature | Exam- To include ( Monthly Progress Tracker 1 to 6, Split Test 1 to 4, Term -1 Progress Tracker, Term -2 Progress Tracker , Half Portion 1 to 3, Full Portion, Pre Board , Revision Test 1 to 6
80 | Academic | Coordinator/ Gayathri | Mark Entry | Missing | Feature | Mark Entry- Entry to be done from Coordinator end as well. Need to give access
81 | Academic | Coordinator/ Gayathri | Sample questions | Missing | Feature | Sample question- Multiple question direct entry to be included with image uploading option to be added to generate Question bank . Selection of chapters and questions filters should also be added for selective download
82 | Academic | Coordinator/ Gayathri | Class | Missing | Feature | Class- (Lesson plan, Student deleverables), Student Evaluation ( Unit Test,, Eaxm, Question Bank)
83 | Academic | Coordinator/ Gayathri | Sample questions | Missing | Feature | Sample question to be renamed as Quesiton Bank
84 | Academic | Coordinator/ Gayathri | SOM | Missing | Feature | SOM list not visible
85 | Academic | Coordinator/ Gayathri | SOM | Change | Feature | SOM bulking uploading to be given. Template to be shared by QMIS
86 | Academic | Coordinator/ Gayathri | My Profile | Change | Feature | Personal Profile -( All staff related details to be brought down under this- Attendance, Leave request)
87 | Academic | Coordinator/ Gayathri | My Profile | Change | Feature | Leave request- View to be enabled for coordinator
88 | Academic | Coordinator/ Gayathri | Student Allocation | Change | Feature | Student allocation access only to Principal
89 | Academic | Coordinator/ Gayathri | Dashboard | Change | Feature | Grouping to be done ( Student / My Profile) - All sub components to be included under this
90 | Academic | Coordinator/ Gayathri | Dashboard | Suggestion | Feature | SOY consolidation- should be done.
91 | Admin | Security Manager/ Karthik | All | Missing | Feature | Renaming to be done
92 | Admin | Security Manager/ Karthik | Add incident information | Change | Feature | Location- remove gender and add location
93 | Admin | Security Manager/ Karthik | Gate pass | Change | Feature | Add gate pass - to be renamed as visitor and to be brought seperately
94 | Admin | Security Manager/ Karthik | New component | Suggestion | Feature | Inward , Outward register content to be included
95 | Admin | Security Manager/ Karthik | Leave request | Missing | Feature | Apply leave request- drop down - Week- off , Permission to be added. Nearby due date, time also to be added- Maximum 2 hour- to be locked
96 | Admin | Security Manager/ Karthik | Announcement | Suggestion | Feature | Entry tab ( Handover- Takeover)- Security hold should also have access
97 | Admin | Security Manager/ Karthik | Incident management | Missing | Feature | Entry point - CSO / Gate keeper - access to be given ( to be renamed)
98 | Admin | Security Manager/ Karthik | Incident management | Missing | Feature | Vendor list to be recorded- with image & document
99 | Audit | Quality Audit/ Sangamitra | Audit Schedule | Missing | Feature | New meeting schedule- Reoccuring schedule to be enabled ( Day & Date - recurring )
100 | Audit | Quality Audit/ Sangamitra | Execute audit | Change | Feature | Remove- Execute audit
101 | Audit | Quality Audit/ Sangamitra | Audit Management | Suggestion | Feature | Create- Audit Components with Rubrics as seperate icon
102 | Audit | Quality Audit/ Sangamitra | Observation- RCA, ATR | Missing | Feature | Root cause analysis & ATR- Accepted/ Declined- Button to be fixed for Quality and Process auditors. If declined, the concern should reoccur to the responsible person
103 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Suggestion | Feature | Set NA as default entry in all entries. (Values from drop down can be selected on need basis)
104 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Missing | Feature | Include in Create observation( Grade , Section, Subject, Component, Sub Component, Rubrics, Duration of Audit, Risk Type, Roll Call issue raised, Value created by this audit risk identification)
105 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Change | Feature | Location is not required in Quality Audit
106 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Change | Feature | Department- Default setting as Acadmics- for Quality Audit. Remove- Responsible department
107 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Change | Feature | Severity- 5 rating to be included
108 | Audit | Quality Audit/ Sangamitra | Observation-Open Observation | Change | Feature | Rename Category to Component and include the comeponet, sub components and its rubrics from GSS shared

## Pending Review
Pending for Review
1 | Security Module
2 | Student Module
3 | DA Module
4 | HR
5 | Audit
6 | Finance

## MD Points
S. No. | Module | Role / User | Screen / Page | Category | Type | Description of Issue / Change
1 | All | General | All | Missing | Feature | File Room Management Yet to see
2 | All | General | All | Missing | Feature | Maintenance Yet to see
3 | All | General | All | Missing | Feature | CCTV Profile Yet to see
4 | All | General | All | Missing | Feature | PRO Yet to develop
5 | All | General | All | Missing | Feature | · Colour coding for all to be revisited and made uniformly
6 | All | General | All | Missing | Feature | · Super Admin access can be given to multiple people as per the requirement
7 | All | General | All | Missing | Feature | · Trend chart in Super Admin Dashboard
8 | All | General | All | Missing | Feature | · Approval- Department Overseer is the approver (Admin- Shalini)
9 | All | General | All | Missing | Feature | · Like DSR, all entries should have a fixed closure time planned in the monthly calendar itself, beyond which data entry is restricted.
10 | All | General | All | Missing | Feature | · Every user will receive notification of their due dates regularly
11 | All | General | All | Missing | Feature | · If wrong data is entered, re-entry approval can be given only by Super Admin and One down of Super Admin.
12 | All | General | All | Missing | Feature | · All approval should be given to only one member of the respective department
13 | Academic | General | All | Missing | Feature | · Time table change approval alone can be given to Principal.
14 | Audit | General | All | Missing | Feature | Compliance Score: All audit deviations should be visible both for Process and Quality
15 | Maintenance | General | All | Missing | Feature | Vehicle Bills and Maintenance list will be visible
16 | Finance | Finance Details |  | Missing | Feature | Finance & Compliance Trend to be renamed as Budgeted Vs Actuals
17 | Finance | Finance Details |  | Missing | Feature | Revenue- Termly and Monthly history visibility Revenue (Budgeted Vs Actuals), Expenses (Budgeted Vs Actuals), Monthly Expenses (Budgeted Vs Actuals- Increase or Decrease). Don’t use Red and Green in common bars and chart. Use Red and Green to show flags.
18 | All | General | All | Missing | Feature | Every aspect of Dashboard should include 3 point rating scale.
19 | Transport | General | All | Missing | Feature | All School fee and Transport fee to be send to ERP team and it should be assigned in the ERP by ERP team only.
20 | Audit | General | All | Missing | Feature | Academics- Process, Quality should be visible separately
21 | All | General | All | Missing | Feature | Inventory- Stores – name should be uniform
22 | All | General | All | Missing | Feature | Canteen, Mess- rename as Café
23 | All | General | All | Missing | Feature | Income Mix- to be renamed
24 | Finance | Finance Details |  | Missing | Feature | All revenue Active Findings by Severity- Total, Findings, Closed , Pending, should be visible. List of Critical should be viewed through linking to the page with highlighted colour of the critical . Specific and detailed critical list should be accessible
25 | All | General | All | Missing | Feature | Department Compliance ranking
26 | All | General | All | Missing | Feature | Each department should be coloured differently- Performance of department should be in 3 colour codes, Average, Above average, Below average
27 | All | Module Health | All | Missing | Feature | User Management- Login history, Device usage will be visible
28 | Stores | Stores |  | Missing | Feature | Critical Inventory Alerts Details-
29 | Stores | Stores |  | Missing | Feature | Stationery Stores, Café is existing. To include the remaining in the list given below
30 | All | Module Health | All | Missing | Feature | Housekeeping (Actuals, Low or High),Laboratory maintenance (Actuals, Low or High), Stationery stores (Actuals, Low or High),Café (Actuals, Low or High)
31 | Transport | Transport |  | Missing | Feature | Transport maintenance (tyre, coils, fibre glass, tool kit etc to be included)- Entry for only actuals
32 | Maintenance | Maintenance |  | Missing | Feature | Building maintenance (wire, light, etc to be included)- Entry for only actuals
33 | All | Module Health | All | Missing | Feature | Alert Type--Stock comparison (Actual requirement, Available stock, Low stock, Excess stock). Near status- view button can be included to get details.
34 | Academic | Student Database | All | Missing | Feature | All attendance should go directly through biometric (School and Transport)
35 | Academic | Student Database | All | Missing | Feature | Total capacity of the bus, students and teachers boarding count. Usage capacity, data comparison for overloaded or shortage.
36 | Academic | Student Database | All | Missing | Feature | Daily or Weekly Trend to be named properly as Daily or Weekly
37 | Academic | Student Database | All | Missing | Feature | Grade 10 to 11 – Readmission students data to be merged. So far it is not yet mapped.
38 | Academic | Student Database | All | Missing | Feature | Entire student’s profile and score should be analysed and should be shown in graph.
39 | Academic | Student Database | All | Missing | Feature | Student score, class average, month wise , year wise comparative analysis data to be given. (1 year, 3 year, 5 year – drop down filter to be placed). Parent and teachers can compare
40 | HR | HR | All | Missing | Feature | Employee Details: Comparison- Performance comparison- BSC and Audit Scores to be included. Description of subject handling to be included
41 | PRM | PRM | All | Missing | Feature | Gate Pass List
42 | PRM | PRM | All | Missing | Feature | Total passes issued to be visible
43 | Transport | Transport | All | Missing | Feature | Fuel- Budgeted Vs Actuals
44 | Transport | Transport | All | Missing | Feature | Fleet wise- maintenance history , standard format to be included
45 | Transport | Transport | All | Missing | Feature | Transport maintenance- Standard format to be included (Total km, Per bus km, etc)
46 | Maintenance | Maintenance | All | Missing | Feature | EB maintenance- Standard format to be included (Sangamitra to meet along with Shalini and Karthik to get the standard formats )
47 | Communication | Communication | All | Missing | Feature | Assing Task List-DSR will be integrated into ERP after understanding the requirement after
48 | User Management | User Management | All | Missing | Feature | Communication- Assigned task from MD will be visible to all Overseers
49 | User Management | User Management | All | Missing | Feature | Login History- File download and print access records should be visible to Super admin
50 | User Management | User Management | All | Missing | Feature | Data change or delete history should be visible to Super admin