## L1 Plan
QMIS School ERP – Month-End Fast-Track Plan ¦ 07-Oct-2026 → 30-Oct-2026 (Go-Live by Month-End)
Source: QMIS ERP Specification & SOPs. Accelerated with AI coding tools (Claude / Gemini agents). Timeline bars are formulas driven by Starting / End Date.
[7 empty] | W1 |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
Sl.No | Task Name | Sub Task Name | Description | Starting Date | End Date | Remarks | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30
1 | Track 1: Foundation & Core Engines | Multi-Campus DB Schema & Master Tables | PostgreSQL schema with mandatory Campus Tag on all tables, UUID keys, academic year masters, and school parameters. | 2026-10-07 | 2026-10-08 | AI-generated Prisma/SQL DDL & ERD diagrams ¦ Tracker: Phase 0 ¦ Depends on Sl.No: –
2 | Track 1: Foundation & Core Engines | Dynamic RBAC & Permission Matrix | Predefined role definitions for all 7 departments; granular View/Create/Approve/Export ACL flags; profile switch logic. | 2026-10-07 | 2026-10-08 | AI boilerplate auth middleware & JWT role guards ¦ Tracker: Phase 0 ¦ Depends on Sl.No: 1
3 | Track 1: Foundation & Core Engines | Universal UIS Core Data Layer | 360-degree lifetime student and staff user profiles, document vault schemas, and sibling association models. | 2026-10-08 | 2026-10-09 | AI schema generation & synthetic mock data injection ¦ Tracker: Phase 0 ¦ Depends on Sl.No: 1
4 | Track 1: Foundation & Core Engines | Dynamic Workflow & Approval Engine | Visual multi-level approval pipeline configuration with financial approval limits and automated 24-hr escalation timers. | 2026-10-08 | 2026-10-09 | AI finite-state-machine (XState/orchestrator) generator ¦ Tracker: Phase 0 ¦ Depends on Sl.No: 2
5 | Track 1: Foundation & Core Engines | Immutable System Audit Logger | Microsecond timestamped event logging capturing logins, data entries, report downloads, prints, and MD message views. | 2026-10-09 | 2026-10-12 | AI audit interceptor middleware & DB change-data-capture ¦ Tracker: Phase 0 ¦ Depends on Sl.No: 1
6 | Track 2: Core Academics & Attendance | eSSL iClock RFID Biometric Receiver | Socket/HTTP push listener for eSSL iClock server (port 99); real-time punch capture, auto-absence, and grace cutoff engine. | 2026-10-12 | 2026-10-13 | AI socket parser & automated mock device punch generator ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 3
7 | Track 2: Core Academics & Attendance | Timetable Generator & Clash Detection | Dynamic weekly class, teacher, and exam schedule builder with conflict avoidance and relief period auto-substitution. | 2026-10-12 | 2026-10-13 | AI constraint satisfaction algorithm for scheduling ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 3
8 | Track 2: Core Academics & Attendance | Dynamic Lesson Planning Engine | Monthly plan authoring (objectives, teaching aids, assessment); 4-tier approval: Teacher → Coord → Principal → DA. | 2026-10-13 | 2026-10-14 | AI UI scaffold matching Oct Lesson Plan template ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 4
9 | Track 2: Core Academics & Attendance | Question Bank & Examination Setup | Question repository by bloom's taxonomy, blueprint authoring, exam timetable creation, and hall ticket generation. | 2026-10-13 | 2026-10-15 | AI question ingestion parser & exam blueprint builder ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 7
10 | Track 2: Core Academics & Attendance | Marks Entry & CBSE Grading Engine | Single/bulk marks upload, moderation approvals, term weightages (CA/RCT, Midterm, Annual), and credit point formulas. | 2026-10-14 | 2026-10-15 | AI formula extraction from Progress Report.xlsm ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 9
11 | Track 2: Core Academics & Attendance | Printable CBSE Report Card Generator | Pixel-perfect automated PDF generation matching official Queen Mira report card format (Aariv Doddi model). | 2026-10-14 | 2026-10-16 | AI PDF template styling via React-PDF / Puppeteer ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 10
12 | Track 2: Core Academics & Attendance | HomeFun (Homework) & Digital Diary | Daily homework assignment dispatch, multimedia attachment support, student submission tracking, and parent viewing. | 2026-10-15 | 2026-10-16 | AI file-uploader & responsive mobile student portal ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 3
13 | Track 2: Core Academics & Attendance | Student Gate Pass & Internal Messaging | PRM/Teacher gate pass workflow with dynamic approver selection and Security scan; one-to-one messaging with MD logging. | 2026-10-15 | 2026-10-16 | AI barcode/QR token generator & chat component ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 4
14 | Track 2: Core Academics & Attendance | Complaints Desk with 24-Hour SLA Escalation | Parent/student complaint ticketing with countdown timer; automated next-tier escalation on 24-hr breach or 'Not Satisfied'. | 2026-10-15 | 2026-10-19 | AI cron-based SLA trigger & alert notification engine ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 4
15 | Track 2: Core Academics & Attendance | Library Management System | Catalogue management, barcode checkout (1 book/student, 5/staff), custom loan duration, missing books log, and overdue fines. | 2026-10-16 | 2026-10-19 | AI book metadata scraper & automated fine calculator ¦ Tracker: Phase 1 ¦ Depends on Sl.No: 3
16 | Track 3: HR & Payroll Engine | Staff Directory & Document Vault | HR-managed employee master, qualification records, document expiry alerts (passport, contract, certifications). | 2026-10-16 | 2026-10-19 | AI schema import from HR Sample statement June 2026 ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 3
17 | Track 3: HR & Payroll Engine | Staff Recruitment & Cross-Dept Interview Panels | Vacancy requisition, applicant tracking, multi-department interview panel scheduling, and consolidated candidate rating rubrics. | 2026-10-19 | 2026-10-20 | AI applicant resume parser & interview scoring UI ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 16
18 | Track 3: HR & Payroll Engine | Staff Onboarding & Automated User Creation | Offer letter generation (Abiramy model), cross-dept onboarding tasks (IT, Stores), and automatic ERP login provisioning. | 2026-10-19 | 2026-10-20 | AI automated welcome email & temporary password reset flow ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 17
19 | Track 3: HR & Payroll Engine | Staff Biometric Attendance & 2-Hour Permissions | Shift timing configuration per department, leave balances (Casual, Sick, Earned), and formal 2-hour permission slips. | 2026-10-19 | 2026-10-21 | AI biometric muster integration with iClock punches ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 6
20 | Track 3: HR & Payroll Engine | Automated Payroll & Payslip Engine | Monthly payroll execution: attendance deductions, PF, ESI, TDS, professional tax, loan repayments, and PDF payslip generation. | 2026-10-20 | 2026-10-21 | AI payroll rules engine based on February Model sheet ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 19
21 | Track 3: HR & Payroll Engine | Staff Incentive Engine (Overtime & Referrals) | Calculation of hourly extra-work incentive from RFID punches, student admission referral bonuses, and staff hiring bonuses. | 2026-10-20 | 2026-10-22 | AI logic matching Compensation Claim SOP form ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 20
22 | Track 3: HR & Payroll Engine | Staff Exit Clearances & Digital Exit Interview | Resignation tracking, digital exit interview questionnaires, multi-department No-Dues clearance, and user deactivation. | 2026-10-21 | 2026-10-22 | AI digital form generator from Exit Interview Questionnaire.pdf ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 18
23 | Track 4: Finance & Accounting Engine | Dynamic Fee Structure & Instalment Rules | Tuition, admission, transport, books, and extra-curricular fees (rifle shooting, karate) with term/monthly instalments and late fees. | 2026-10-16 | 2026-10-19 | AI fee rule configuration builder & late fee calculator ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 1
24 | Track 4: Finance & Accounting Engine | Counter Fee Collection & Serialised Receipts | Cashier collection terminal, partial payment support, sibling/staff-child concessions, and instant tax invoice receipt prints. | 2026-10-19 | 2026-10-20 | AI POS counter UI with offline resilience ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 23
25 | Track 4: Finance & Accounting Engine | Paytm EDC POS & Online Payment Gateway | Paytm swipe machine webhook sync for counter card/UPI payments and online parent portal gateway integration. | 2026-10-20 | 2026-10-21 | AI Paytm API webhook listener & reconciliation handler ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 24
26 | Track 4: Finance & Accounting Engine | WhatsApp Business API Cloud Integration | Automated dispatch of fee bills, due reminders with payment links, fee receipts, and attendance absence alerts via WhatsApp. | 2026-10-20 | 2026-10-21 | AI WhatsApp Cloud API message template dispatcher ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 24
27 | Track 4: Finance & Accounting Engine | Departmental Budgets & Role Spending Thresholds | Annual/monthly budget allocations per department head and school event; automatic re-routing of requests exceeding limits. | 2026-10-21 | 2026-10-22 | AI budget ceiling interceptor & approval routing ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 4
28 | Track 4: Finance & Accounting Engine | Payment Vouchers & General Ledgers | Maker-checker invoice voucher verification, automated double-entry ledger postings, and bulk bank NEFT transfer export. | 2026-10-21 | 2026-10-23 | AI double-entry accounting engine & ledger generator ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 27
29 | Track 4: Finance & Accounting Engine | Bank Reconciliation Statement Engine | Bank statement CSV/Excel parser, automated transaction matching against cashbook ledgers, and variance reporting. | 2026-10-22 | 2026-10-23 | AI fuzzy matching algorithm for bank reconciliation ¦ Tracker: Phase 2 ¦ Depends on Sl.No: 28
30 | Track 5: Non-Academics & Operations | Central Stores & Returnable Asset Tracking | SKU catalogue, inventory master, minimum reorder thresholds, and issue ledgers distinguishing returnable equipment. | 2026-10-21 | 2026-10-23 | AI inventory tracker & barcode stock audit UI ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 3
31 | Track 5: Non-Academics & Operations | 3-Vendor Store Procurement Workflow | Store requisition -> 3 vendor quotations comparison -> JD endorsement -> Finance budget verification -> PO & GRN creation. | 2026-10-22 | 2026-10-26 | AI quotation comparator & PO document generator ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 30, 27
32 | Track 5: Non-Academics & Operations | Operational Helpdesk Ticketing Engine | Categorised service requests (IT Support, Electrical, Plumbing, Cleaning) with automated 24-hr SLA escalation to JD/MD. | 2026-10-22 | 2026-10-26 | AI ticketing workflow & mobile technician dispatch ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 14
33 | Track 5: Non-Academics & Operations | Transport Fleet, Routes & Bus Allocations | Bus catalogue, route stops, driver/conductor duty allotment, and student transport roster linked with Finance fee status. | 2026-10-23 | 2026-10-26 | AI route clustering & student stop assignment tool ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 23
34 | Track 5: Non-Academics & Operations | Driver / Conductor Mobile Trip Portal | Simplified mobile PWA for drivers/conductors: Home pickup and School drop trips with 1-tap student boarding/drop check. | 2026-10-23 | 2026-10-27 | AI mobile PWA UI scaffold optimized for low-end phones ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 33
35 | Track 5: Non-Academics & Operations | Live School Bus GPS Tracking Integration | Vendor telematics ingestion mapping live bus coordinates onto map overlays for parents' student profile and Transport Mgr. | 2026-10-26 | 2026-10-27 | AI Mapbox/Leaflet live telemetry map renderer ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 33
36 | Track 5: Non-Academics & Operations | Security Visitor Management with Photo Badges | Visitor check-in (name, mobile, photo, host), automatic PRM host notification, and barcode visitor badge printing. | 2026-10-26 | 2026-10-27 | AI webcam photo capture component & badge printer ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 13
37 | Track 5: Non-Academics & Operations | Camera Room CCTV & File Room Vault | CCTV incident footage marking & chain-of-custody request workflow; File Room physical archive with granular confidentiality tags. | 2026-10-26 | 2026-10-28 | AI video metadata indexing & document security tags ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 4
38 | Track 5: Non-Academics & Operations | PRO Government Liaison & CBSE Compliance | Tracker for statutory licenses, CBSE affiliation inspections, fire safety renewals, building permits, and challan payments. | 2026-10-26 | 2026-10-28 | AI statutory compliance calendar & deadline alert engine ¦ Tracker: Phase 3 ¦ Depends on Sl.No: 3
39 | Track 6: Audit Automation & Compliance | Automated Audit Scheduler Engine | Replaces all 20+ legacy Google Sheets: auto-generates recurring daily, weekly, monthly audit tasks per master annual plan. | 2026-10-26 | 2026-10-27 | AI scheduler migrating Annual Plan and checkpoints.xlsx ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 4
40 | Track 6: Audit Automation & Compliance | 38 Daily Process Audit Inspection Checklists | Digital inspection forms: roll call audit, biometric sync checks, DSR entries, GPS tracking, washroom rounds, sickbay checks. | 2026-10-26 | 2026-10-28 | AI digital checklist builder from Process Audit 2025-26.xlsx ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 39
41 | Track 6: Audit Automation & Compliance | Academic Quality Audits (SPQA / PQA) | Classroom teaching observations, lesson plan adherence, student notebook correction audits, and exam paper evaluations. | 2026-10-27 | 2026-10-28 | AI rubric scoring forms from Quality Audit 2025-26.xlsx ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 39
42 | Track 6: Audit Automation & Compliance | CAPA Resolution & ATR Evidence Engine | Non-conformance risk classification (Critical, Major, Minor), CAPA assignment with deadlines, and Action Taken Reports (ATR). | 2026-10-27 | 2026-10-29 | AI CAPA remediation workflow & photo evidence verification ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 40
43 | Track 6: Audit Automation & Compliance | Balanced Scorecard (BSC) Scoring Engine | Automated scoring combining operational compliance, audit results, and HOD evaluations; exported directly to HR appraisals. | 2026-10-27 | 2026-10-29 | AI BSC KPI calculation engine ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 41, 20
44 | Track 7: MD Executive Cockpit | MD Panoramic Executive Dashboard | Cross-department executive cockpit: live enrollment, daily attendance %, fee collections vs targets, open tickets, audit score. | 2026-10-28 | 2026-10-29 | AI executive KPI data aggregator & interactive charts ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 10, 20, 24, 40
45 | Track 7: MD Executive Cockpit | MD Unified Final Approvals Centre | Centralised single approval queue for high-value purchase orders, staff loans, terminations, student TCs, and CCTV footage. | 2026-10-28 | 2026-10-29 | AI consolidated approval widget with mobile authorization ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 4, 31
46 | Track 7: MD Executive Cockpit | MD Message Oversight & Audit Logging | Authorized executive oversight of internal user-to-user messaging with mandatory logging of viewing events in the audit trail. | 2026-10-28 | 2026-10-29 | AI secure conversation viewer with immutable access log ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 13, 5
47 | Track 7: MD Executive Cockpit | 8:00 AM Automated Executive Daily Digest | Automated daily morning summary email and push notification delivering critical institutional vitals to MD at 8:00 AM. | 2026-10-28 | 2026-10-29 | AI scheduled cron report generator & HTML email digest ¦ Tracker: Phase 4 ¦ Depends on Sl.No: 44
48 | Track 8: Polish, Migration & Go-Live | Star of the Month (SOM) & Gamification | Holistic rubric scoring (academics, behaviour, values) based on Grade 2A/2B and KG SOM models; peer star rating system. | 2026-10-28 | 2026-10-29 | AI SOM scoring algorithm from SOM Excel sheets ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 10
49 | Track 8: Polish, Migration & Go-Live | Legacy Excel Data Migration & Ingestion | Automated ETL pipelines importing historical student records, staff rosters, attendance logs, and fee balances from legacy files. | 2026-10-28 | 2026-10-29 | AI data transformation scripts parsing legacy spreadsheets ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 1, 16
50 | Track 8: Polish, Migration & Go-Live | End-to-End Automated Testing & Security Audit | Automated regression suites covering role permissions, financial approvals, biometric syncs, and 24-hr escalation triggers. | 2026-10-29 | 2026-10-30 | AI Playwright/Jest test generation & OWASP security scan ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 44, 49
51 | Track 8: Polish, Migration & Go-Live | Staging UAT & Key Stakeholder Pilot Demo | Deployment to staging environment; walkthroughs with Director of Academics, Joint Director, HR, Finance Head, and JD Audit. | 2026-10-29 | 2026-10-30 | Live stakeholder validation across pilot classes ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 50
52 | Track 8: Polish, Migration & Go-Live | Production Deployment & Disaster Recovery Test | Production infrastructure provisioning, SSL/domain setup, automated backup test restore, and database indexing. | 2026-10-30 | 2026-10-30 | Automated Terraform/Docker deployment & backup drill ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 51
53 | Track 8: Polish, Migration & Go-Live | Production Go-Live & Official Cutover | Live cutover from legacy Google Sheets / Edumerge; official operational handover to Queen Mira International School. | 2026-10-30 | 2026-10-30 | Official institutional launch & live system sign-off by Month-End ¦ Tracker: Phase 5 ¦ Depends on Sl.No: 52
Summary
Total sub-tasks
AI Accelerated Build
| Track 1: Foundation & Core Engines | 5
| Track 2: Core Academics & Attendance | 10
| Track 3: HR & Payroll Engine | 7
| Track 4: Finance & Accounting Engine | 7
| Track 5: Non-Academics & Operations | 9
| Track 6: Audit Automation & Compliance | 5
| Track 7: MD Executive Cockpit | 4
| Track 8: Polish, Migration & Go-Live | 6
Programme start
Final delivery (Go-Live by Month-End)
Working days